## Test summary report
Tester | VLVTu
Date | 2025-07-22

## Bug Report
Defect ID | Defect Title | Defect Description | Function ID | Severity | Reported By | Date Reported | Status | Comment
GUI Testing
B001 | "Home" link in the header navigates to the wrong page | Steps to Reproduce: 1. Navigate to home page on the website. 2. Click on the 'Home' link in the navigation bar. Expected Result: The user is redirected to the Homepage. Actual Result: The user is redirected to the contact page ('/contact'). | Home Page | High | VLVTu | 2025-07-21 | Open | Critical navigation flaw that negatively impacts user experience.
B002 | Navigation bar link hover color lacks sufficient contrast | Steps to Reproduce: 1. Navigate to home page on the website. 2. Hover the mouse cursor over any link in the navigation bar. Expected Result: The link text color should change clearly to indicate it is being hovered over. Actual Result: The text color changes, but the contrast is too low, making it difficult to distinguish from the original color. | Home Page | Low | VLVTu | 2025-07-21 | Open | Usability issue. Should be improved for better visual feedback.
B003 | Website logo in the top-left corner is not displayed correctly | Steps to Reproduce: 1. Navigate to home page on the website. 2. Observe the logo in the top-left corner. Expected Result: The website logo is displayed clearly and correctly. Actual Result: The logo is broken or fails to load, showing a missing image icon. | Home Page | Medium | VLVTu | 2025-07-21 | Open | Affects brand identity and the site's professional appearance.
B004 | Search icon is not displayed corectly | Steps to Reproduce: 1. Navigate to home page on the website. 2. Observe icon of the search section. Expected Result: The icon is displayed clearly and correctly. Actual Result: The icon is broken or fails to load, showing a missing image icon. | Home Page | Low | VLVTu | 2025-07-21 | Open | Affects the users' experience and create an ambiguous interface.
B005 | Product sorting logic is inverted | Steps to Reproduce: 1. Navigate to home page on the website. 2. Apply the "Name (A - Z)" sort option. 3. Apply the "Price (High - Low)" sort option. Expected Result: Sorting by "Name (A - Z)" should list products alphabetically. Sorting by "Price (High - Low)" should list products from most to least expensive. Actual Result: Sorting by "Name (A - Z)" lists products in Z-A order. Sorting by "Price (High - Low)" lists products from low to high. | Home Page | High | VLVTu | 2025-07-21 | Open | Critical bug. A core feature is behaving the opposite of its description.
B006 | Search function is not placed in an intuitive location | Steps to Reproduce: 1. Navigate to home page on the website. 2. Attempt to locate the search bar. Expected Result: The search function should be in a standard, easily discoverable position (e.g., top-right of the header). Actual Result: The search function is placed in a non-standard location, making it difficult for users to find. | Home Page | Low | VLVTu | 2025-07-21 | Open | Poor placement impacts usability, though the feature itself may work.
B007 | Search input does not provide suggestions | Description: The search functionality lacks an autocomplete or suggestion feature. When a user types in the search box, the system does not offer suggestions to help them complete their query or discover related terms. | Home Page | Low | VLTu | 2025-07-21 | Open | This is a missing enhancement that is standard on modern websites.
B008 | Spelling mistakes present in various titles | Steps to Reproduce: 1. Navigate to home page on the website. 2. Read the titles on pages and in different sections. Expected Result: All text content should be professionally written and free of spelling errors. Actual Result: There are multiple spelling mistakes in titles across the site. | Home Page | Low | VLVTu | 2025-07-21 | Open | Affects the professionalism and credibility of the website.
B009 | Item lists are not sorted by default | Description: Many lists within the application (e.g., dropdowns, category lists) are not sorted in a logical order (e.g., alphabetically). This forces users to manually scan the entire list to find an item, which is inefficient. | Home Page | Medium | VLVTu | 2025-07-21 | Open | Affects usability, especially for long lists.
B010 | No progress indicators are shown for long-running tasks | Description: When the system performs a time-consuming action (e.g., page load, file upload), there is no visual feedback (like a spinner or loading bar). This makes the website feel unresponsive or frozen, potentially causing users to click away or repeat the action. | Home Page | Medium | VLVTu | 2025-07-21 | Open | Poor feedback degrades the perceived performance of the site.
Usability Testing
B001 | Search bar is placed in a non-standard, undiscoverable location | Description: The main site search bar is located within the left-hand filter sidebar instead of the global header. User Expectation: Users expect the primary search bar to be in a prominent location like the page header for easy access. Actual Result: The search bar is difficult to discover, leading to user frustration. 5 out of 7 test participants first looked for it in the header. | Search &Filter | High | VLVTu | 2025-07-21 | Open | Violates Jakob's Law of web conventions. A key navigation tool is effectively hidden from most users on first glance.
B002 | Ambiguous interaction model: No clear action to apply filters | Steps to Reproduce: 1. Go to the Home Page where the filter function is at. 2. Select a filter checkbox (e.g., "Hand Saw"). Expected Result: The page should either update automatically with a clear loading indicator, or there should be an "Apply Filters" button to confirm the selection. Actual Result: There is no visual feedback. Users are unsure if the filter has been applied, leading to confusion and lack of confidence. | Search &Filter | High | VLVTu | 2025-07-21 | Open | This ambiguity breaks the core filtering workflow and forces users to guess, creating a frustrating experience.
B003 | Filter categories use a non-scalable flat list design | Description: The "By category" and "By brand" filter sections are displayed as a single, long list of checkboxes. Expected Result: Filter groups should use a scalable UI pattern, such as a collapsible accordion, to handle a growing number of options. Actual Result: The current design will become cluttered and difficult to scan as more filters are added, increasing cognitive load and degrading usability over time. | Search &Filter | Medium | VLVTu | 2025-07-21 | Open | The current design is not future-proof and will become a significant usability problem as inventory grows.
B004 | Typo in the sort dropdown label ("Sorth" and "Serch") | Steps to Reproduce: 1. View the filter bar and search bar. 2. Look at the label for the sort dropdown menu at the top of the product grid. Expected Result: The label should be "Sort" and "Search" Actual Result: The label is misspelled as "Sorth" and "Serch". | Search &Filter | Low | VLVTu | 2025-07-21 | Open | Simple copy error that affects the site's professionalism and user trust.
B005 | Poor visual distinction between 'Sort' and 'Filter' controls | Description: The "Sort" dropdown and the main "Filters" section are placed in close proximity without sufficient visual separation, causing some users to be confused about their distinct functions. Expected Result: There should be a clearer visual hierarchy (e.g., spacing, dividing line) to help users immediately differentiate between sorting and filtering. Actual Result: The lack of separation slightly increases cognitive load. | Search &Filter | Low | VLVTu | 2025-07-21 | Open | A minor UI refinement is needed to improve clarity and usability.
Cross-platform Testing
There is no defects due to platform difference.