## Test Summary Report
TEST REPORT
Project Name |  | practice-software-testing |  |  | Creator |  | Cao Uyển Nhi
Group ID |  | 7 |  |  | Approver |  | Cao Uyển Nhi
Note
| Test Coverage | 100% |  |  |  |  | Date: | 2025-08-21
| Successful Coverage | 51.11%
No. | Items | Tested | Passed | Failed | Blocked | Skipped | Not yet tested | Total | Test Coverage
1 | Payment Check API | 30 | 7 | 23 | 0 | 0 | 0 | 30 | 100%
2 | Brands API | 30 | 12 | 18 | 0 | 0 | 0 | 30 | 100%
3 | Favourite API | 30 | 27 | 3 | 0 | 0 | 0 | 30 | 100%
| Total | 90 | 46 | 44 | 0 | 0 | 0 | 90 | 100%

## Defect Severity Distribution
DEFECT SEVERITY DISTRIBUTION
No. | Items | Fatal | Serious | Medium | Cosmetic | Total
1 | Payment Check API | 0 | 3 | 20 | 0 | 23
2 | Brands API | 0 | 2 | 16 | 0 | 18
3 | Favourite API | 0 | 0 | 3 | 0 | 3
4 |  | 0 |  |  |  | 0
5 |  | 0 |  |  |  | 0
| Total | 0 | 5 | 39 | 0 | 44