## Test summary report
Tester | VLVTu
Date | 2025-08-02

## Bug report
Bug ID | Defect Title | Steps to Reproduce | Function ID | Expected Result | Actual Result | Priority | Severity | Reported By | Date Reported | Status | Comment
B001 | First Name and Last Name fields are swapped on Profile page | 1. Log in as a user. 2. Navigate to the Profile page. 3. Observe the data displayed in the "First Name" and "Last Name" fields. | UC01 | Correct information is displayed in the right field (First Name in "First Name" field, Last Name in "Last Name" field). | - First name is displayed in the "Last Name" field. - Last name is displayed in the "First Name" field. | High | Major | VLVTu | 2025-06-08 | Open
B002 | Updating any user profile field fails with "Resource not found" error | 1. Navigate to the Profile page. 2. Enter any valid data into a field (e.g., enter "John" in the "First Name" field). 3. Click the "Update Profile" button. (This issue affects test cases TC101 through TC126) | UC01 | The profile should be updated successfully and a success message should be displayed. | An error is displayed: "Resource not found". The profile is not updated. | Highest | Blocker | VLVTu | 2025-06-09 | Open
B003 | Successful password change action locks the user out of the account | 1. Navigate to the Profile page. 2. Enter a valid current password. 3. Enter a new, valid password that meets all complexity criteria (e.g., 'StrongN3wP@ssword!'). 4. Confirm the new password. 5. Click "Update Password". 6. Log out and attempt to log in with the new password. (This issue affects test cases TC127, TC130, TC131, TC132, TC133, TC134) | UC01 | 1. A success message is displayed. 2. The user is able to successfully log in with the new password. The old password no longer works. | 1. A success message is displayed, indicating the password was changed. 2. The user cannot log in with the new password. The old password also fails. The user is effectively locked out. | Highest | Critical | VLVTu | 2025-06-10 | Open
B004 | Updating an order's status incorrectly updates all other orders with the same original status | 1. Go to the Order list page. Ensure multiple orders exist with the same status (e.g., "SHIPPED"). 2. Click "Edit" on one of these orders (e.g., INV-2022000002). 3. On the Order Detail page, change the status to a new value (e.g., "COMPLETED"). 4. Click "Update status". 5. Navigate back to the Order list page. 6. Observe the statuses of all orders that were originally "SHIPPED". (Based on TC208) | UC02 | Only the status for the edited order (INV-2022000002) should change to "COMPLETED". All other orders should retain their original status. | The status of the edited order is updated correctly, but all other orders that also had the original status ("SHIPPED") are also incorrectly updated to "COMPLETED". | High | Major | VLVTu | 2025-06-11 | Open